## PROJECT PLAN
PROJECT PLAN Objective: Secure employment or contract (freelance) work as a VA by 30 November, 2024. | time axis 2024-10-16 to 2025-01-26
Deliverables | Owner | Start Date | End Date | Status
Complete week 4 Milestones | Me | 2024-10-16 | 2024-10-20 | In Progress | 2024-10-16: In Progress; 2024-10-17: In Progress; 2024-10-18: In Progress; 2024-10-19: In Progress; 2024-10-20: In Progress
Start working on week 5 modules | Me | 2024-10-20 | 2024-10-24 | Not started | 2024-10-20: Not started; 2024-10-21: Not started; 2024-10-22: Not started; 2024-10-23: Not started; 2024-10-24: Not started
Complete week 5 Milestones | Me | 2024-10-24 | 2024-10-27 | Not started | 2024-10-24: Not started; 2024-10-25: Not started; 2024-10-26: Not started; 2024-10-27: Not started
Start working on week 6 modules | Me | 2024-10-27 | 2024-10-31 | Not started | 2024-10-27: Not started; 2024-10-28: Not started; 2024-10-29: Not started; 2024-10-30: Not started; 2024-10-31: Not started
Complete week 6 Milestones | Me | 2024-10-31 | 2024-11-03 | Not started | 2024-10-31: Not started; 2024-11-01: Not started; 2024-11-02: Not started; 2024-11-03: Not started
Start working on week 7 modules | Me | 2024-11-03 | 2024-11-07 | Not started | 2024-11-03: Not started; 2024-11-04: Not started; 2024-11-05: Not started; 2024-11-06: Not started; 2024-11-07: Not started
Complete week 7 Milestones | Me | 2024-11-07 | 2024-11-10 | Not started | 2024-11-07: Not started; 2024-11-08: Not started; 2024-11-09: Not started; 2024-11-10: Not started
Start working on week 8 modules | Me | 2024-11-10 | 2024-11-14 | Not started | 2024-11-10: Not started; 2024-11-11: Not started; 2024-11-12: Not started; 2024-11-13: Not started; 2024-11-14: Not started
Complete week 8 Milestones | Me | 2024-11-14 | 2024-11-17 | Not started | 2024-11-14: Not started; 2024-11-15: Not started; 2024-11-16: Not started; 2024-11-17: Not started
Graduation | ALX | 2024-11-26 | 2024-11-26 | Not started | 2024-11-26: Not started
Develop a niche market plan | Me | 2024-11-27 | 2024-11-30 | Not started | 2024-11-27: Not started; 2024-11-28: Not started; 2024-11-29: Not started; 2024-11-30: Not started
Create a Portfolio | Me | 2024-12-01 | 2024-11-07 | Not started
Apply for Virtual Assistant roles | Me | 2024-11-07 | 2024-11-29 | Not started | 2024-11-07: Not started; 2024-11-08: Not started; 2024-11-09: Not started; 2024-11-10: Not started; 2024-11-11: Not started; 2024-11-12: Not started; 2024-11-13: Not started; 2024-11-14: Not started; 2024-11-15: Not started; 2024-11-16: Not started; 2024-11-17: Not started; 2024-11-18: Not started; 2024-11-19: Not started; 2024-11-20: Not started; 2024-11-21: Not started; 2024-11-22: Not started; 2024-11-23: Not started; 2024-11-24: Not started; 2024-11-25: Not started; 2024-11-26: Not started; 2024-11-27: Not started; 2024-11-28: Not started; 2024-11-29: Not started
Secure an employment | Me | 2024-11-30 | 2024-11-30 | Not started | 2024-11-30: Not started